## About
Summary : | This excel document serves as the project timeline for the Smash Ultimate Character Quiz web app. The TASKS tab is the abbrieviated version with just the tasks and dates to be completed. The Tasks breakdown tab has a bit more information for each tasks such as its objectives and who will be completing it.

## TASKS
CS 275: Smash Quiz
TASKS | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
Week 7 | February 18th |  | 25% | 0
Finalize Quiz Questions |  | Friday, 2/22/19 | 50% | 0
Finish Tag System |  | Friday, 2/22/19 | 75% | 0
Begin creating algorithm | Thursday, 2/21/19 |  | 0% | 0
Begin developing client side | Wednesday, 2/20/19 |  | 0% | 0
Begin developing server | Wednesday, 2/20/19 |  | 25% | 0
Begin developing dataases | Wednesday, 2/20/19 |  | 0% | 0
Week 8 | February 25th |  | 0% | 0
Finish quiz algorithm |  | Tuesday, 2/26/19 | 0% | 0
Finish Developing server |  | Sunday, 3/3/19 | 0% | 0
Finish developing necessary databases |  | Sunday, 3/3/19 | 0% | 0
Finish developing client side |  | Sunday, 3/3/19 | 0% | 0
Week 9 | March 4th |  | 0% | 0
Begin working on final presentation | Tuesday, 3/5/19 |  | 0% | 0
Request and receive data from database to server |  | Friday, 3/8/19 | 0% | 0
Request and receive data from server to client |  | Friday, 3/8/19 | 0% | 0
Display quiz results to webpage |  | Friday, 3/8/19 | 0% | 0
Week 10 | March 11th |  | 0% | 0
Finish final presentation |  | Thusday, 3/14/19 | 0% | 0
Implement error handling | Tuesday, 3/12/19 |  | 0% | 0
Begin user testing | Tuesday, 3/12/19 |  | 0% | 0
Finals Week | March 18th |  | 0% | 0
Finalize error handling |  | Monday, 3/18/19 | 0% | 0
Finish user testing |  | Monday, 3/18/19 | 0% | 0
Prepare for final presentation |  | Tuesday, 3/19/19 | 0% | 0

## Tasks Breakdown
Task | Objectives | Start | Finish | Who
Week 7 |  | Monday, 2/18
Finalize Quiz Questions | 1. Create all quiz questions |  | Friday, 2/22 | Everyone
Finish Tag System | 1. Finalize ranking player attributes 2. Understand how characters are tagged |  | Friday, 2/22 | Everyone
Begin creating algorithm | 1. Integrate tag system with the quiz | Thursday, 2/21 |  | Everyone
Begin developing client side | 1. Have some GUI mockups ready 2. Develop necessary webpages 3. Implement quiz questions and ability to chose answers 4. Basic JS | Wednesday, 2/20 |  | Chris (maybe Blake)
Begin developing server | 1. Basic functionality and think of .get uses | Wednesday, 2/20 |  | Hoang
Begin developing databases | 1. Start importing characters and attributes | Wednesday, 2/20 |  | Carter
Week 8 |  | Monday, 2/25
Finish quiz algorithm | 1. Completion of quiz results in user getting top 5 compatible characters |  | Tuesday, 2/26 | Everyone
Finish Developing server | 1. Host all html files 2. Know what .get paths the client will make requests to 3. Know how to get information from databases |  | Sunday, 3/3 | Hoang
Finish developing necessary databases | 1. Add all rankings to each character's attributes 2. Have all databases necessary for quiz |  | Sunday, 3/3 | Carter
Finish developing client side | 1. Make all webpages look pretty 2. Completely implement quiz questions 3. Implement algorithm 4. Have necessary information to make request to server (i.e. URL |  | Sunday, 3/3 | Chris (maybe Blake)
Week 9 |  | Monday, 3/4
Begin working on final presentation | 1. Create powerpoint -> add title slides needed 2. Assign speaking roles | Tuesday, 3/5 |  | Blake (and everyone)
Request and receive data from database to server | 1. Send request for information to database 2. Have database process request, get information, send back to server 3. Have server process and handle information |  | Friday, 3/8 | Carter and Hoang
Request and receive data from server to client | 1. Send request from client to server (ajax and .get) 2. Have server process request, get info from database, send back to client (res.send json data) |  | Friday, 3/8 | Hoang and Chris
Display quiz results to webpage | 1. Process response from server (parse json data.xxx.yyy) 2. Store and display information to webpage (using jquery) |  | Friday, 3/8 | Chris
Week 10 |  | Monday, 3/11
Finish final presentation | 1. Add content to slides 2. Rehearse final presentation |  | Thursday, 3/14 | Mainly Blake but also everyone
Implement error handling | 1. Handle cases of bad input? (i.e. not all questions answered) | Tuesday, 3/12 |  | Mainly Chris but also Everyone
Begin user testing | 1. Test for errors/bugs 2. Test bad input, requests, etc. 3. Make sure quiz works | Tuesday, 3/12 |  | Blake
Finals Week |  | Monday, 3/18
Finalize error handling | 1. Code handles all cases of potential error |  | Monday, 3/18 | Everyone
Finish user testing | 1. Ensure everything works |  | Monday, 3/18 | Everyone
Prepare for final presentation | 1. Rehearse final presentation 2. Chew gum and kick ass |  | Tuesday, 3/19 | Everyone